## Stakeholder Analysis Data
Stakeholder | Stakeholder Role | Power | Interest
Program Manager | Oversees the entire fitness program, makes decisions, and ensures the program stays on track. | 10 | 10
Administrative Coordinator | Manages participant registrations, ensuring all necessary information is collected, and keeping track of enrollments and participant data. | 5 | 5
Marketing Team | Responsible for creating and executing the promotional strategy, handle enrollment, and manage public relations. | 6 | 6
Program Sponsor | Responsible for securing resources (budget, personnel), supporting the program’s objectives, and provide financial or material support for the program. | 9 | 6
Health & Safety Officer | They are responsible for risk assessments and developing emergency procedures in case of accidents. | 7 | 6
Participants | Engage in the fitness program and work toward fitness goals. | 5 | 10
Insurance Providers | Provide coverage for any potential injuries or incidents during the program. | 6 | 4
Fitness Trainers | Deliver fitness sessions, provide guidance, and ensure safety during exercises. | 9 | 10
Nutritionists/Dietitans | Provide dietary guidance and meal plans to ensure participants are eating appropriately for their fitness goals. | 7 | 7

## Stakeholder Analysis Map
WARNING: There is a known bug in Excel where it does not update scatterplot data labels. To manually update the labels: 1) Go to Format Data Labels; 2) Click on the "Reset Label Text" button; 3) Uncheck the "Value from Cells" box; 4) Re-check the "Value from Cells" box.

## Stakeholder & Comm Log
Stakeholder Name | Stakeholder Organization | Role | Top Priority | Contributions Needed? | Expectations of the Project? | Stakeholder Management Strategy | Information Needed | Frequency | Medium
Program Manager | Intenral (Project Team) | Oversees the entire fitness program, makes decisions, and ensures the program stays on track. | Successful program execution and achieving fitness goals | Yes, ensuring the program stays on track and within budget | High-quality results, smooth operations, positive participant feedback | Frequent check-ins to ensure alignment with project goals and timelines | Weekly progress reports, participant feedback, financial updates | Weekly | Email, Meetings
Administrative Coordinator | Internal (Project Team) | Manages participant registrations and logistical support | Ensure smooth registration and onboarding of participants. | Yes, to maintain accurate records and ensure seamless enrollment process. | Seamless registration process, complete participant information | Ongoing check-ins and assistance with any registration issues. | Registration numbers, program updates, participant info, deadlines. | Weekly | Email, meetings, CRM
Marketing Team | Internal (Marketing Department) | Promote the fitness program, handle enrollment, and manage public relations. | Drive enrollments, enhance brand visibility | Yes, creating promotional materials, managing social media, running ads | High participant enrollment, strong program branding and visibility | Regular updates on enrollment numbers, social media engagement | Enrollment data, marketing performance analytics | Bi-weekly | Email, Meetings
Program Sponsor | External (Corporate Sponsors) | Provide financial or material support for the program. | ROI, brand exposure, successful program delivery | Yes, financial contributions, event sponsorship | Brand exposure, high program visibility, measurable impact | Monthly updates on program progress, media coverage, participant engagement | Program progress, participant numbers, media exposure | Monthly | Email, Reports
Health & Safety Officer | Externall (Contractor/ Consultant) | Responsible for safety protocols and risk management | Ensure the safety of participants during fitness activities. | Yes, to develop and enforce health and safety guidelines. | Uphold health and safety standards, minimized risks | Regular check-ins to ensure safety protocols are being followed and adjustments are made if needed. | Program schedules, participant health info (as necessary), incident reports. | Weekly | Meetings, Email, Safety reports
Particpants | External (Porgram attendees) | Engage in the fitness program and work toward fitness goals. | Achieve fitness goals and improve health | Yes, active participation, commitment to fitness plan | Positive experience, clear progress toward goals, motivating instructors | Regular updates on progress and any modifications to the program | Personal progress, new class offerings, event details | Weekly | Email, App
Insurance Provider | External | Provide coverage for any potential injuries or incidents during the program. | Risk management and coverage for incidents | Yes, insurance for events, ensuring all participants are covered | Minimal claims, safety during events, proactive risk management | Periodic updates on risk assessments, incident reports, insurance claims | Incident reports, event schedules, participant counts | As needed | Email, Phone
Fitness Trainers | External (Contracted Professionals) | Deliver fitness sessions, provide guidance, and ensure safety during exercises. | Participant safety, engagement, and fitness outcomes | Yes, program delivery, monitoring participant progress, ensuring safety | Safe, effective workouts and positive participant feedback | Regular communication to address any concerns, discuss class progress | Participant progress, safety protocols, exercise schedules | Daily (during classes) | In-person, WhatsApp
Nutiritionists / Dietitions | External (Contracted Professionals) | Provide dietary guidance and meal plans to ensure participants are eating appropriately for their fitness goals. | Ensure participants have the right nutrition for fitness goals | Yes, offering guidance on meal planning, conducting consultations | Effective dietary guidance, participant engagement with nutrition plans | Coordinate with trainers to ensure dietary plans align with workouts | Dietary plans, participant dietary preferences, health goals | Bi-weekly | Email, In-person

## Drop Down (hidden)
Priority | Management Strategy
Scope | Keep Satisfied
Cost | Manage Closely
Time | Provide General Information
Keep Informed