## Risk Log
Risk # | WBS Entry | Risk Statement | Risk Owner | Probability | Impact | Risk Level | Response Strategy | Response Description | Residual Probability | Residual Impact | Residual Risk Level | Status
1 | 1.1 | Particpant may drop out of program due to lack of motivation | Program Manager | Likely | Moderate | High | Mitigate | Implement a buddy system, set small milestones, and offer rewards to keep participants motivated | Probable | Moderate | Medium | Open
2 | 1.2 | Budget overruns due to unforeseen costs | Project Manager | Probable | Major | Medium | Transfer | Allocate contingency funds and work with vendors to secure fixed prices | Unlikely | Major | Medium | Open
3 | 2.2 | Issues with participant data privacy and security | Program Manager | Probable | Major | Medium | Mitigate | Ensure secure storage of personal data, follow privacy laws, and restrict access to sensitive information | Unlikely | Major | Medium | Closed
4 | 2.3 | Particpiant may experience overexertion and exhaustion | Fitness Trainer | Probable | Major | High | Avoid | Educate particpants about pacing, encourage breaks, and monitor heart rate during workouts | Unlikely | Major | Medium | Open
5 | 3.1 | Severe weather conditions may disprupt scheduled outdoor activities | Event coordinator | Likely | Moderate | High | Transfer | Organize insurance for weather-related conacellations and have indoor alternative available | Unlikely | Moderate | Medium | Open
6 | 3.2 | Inadequate participant attendance due to scheduling conflicts | Program Manager | Likely | Moderate | Medium | Avoid | Send reminders, offer flexible scheduling, and encourage early registration | Unlikely | Moderate | Medium | Open
7 | 4.1 | Venue setup may be delayed due to logistical issues | Event Coordinator | Likely | Moderate | Medium | Mitigate | Ensure early arrival for setup and coordination with venue staff to troubleshoot any issues | Unlikely | Moderate | Medium | Open
8 | 5.2 | Particpants may sustain injuries from equipment misuse | Fitness Trainer | Probable | Major | High | Mitigate | Trainers will deomonstrate proper use of equipment and supervise all exercise | Unlikely | Major | Medium | Open
9 | 5.5 | Delays in project documentation and reporting | Project Manager | Unlikely | Major | Medium | Mitigate | Allocate time for regular check-ins and progress updates to ensure documentation is on track | Unlikely | Moderate | Medium | Closed

## Drop Downs (hidden)
Probablilty | Impact | Risk Level | Response | Status
Rare | Trivial | Low | Avoid | Open
Unlikely | Minor | Medium | Accept | Closed
Probable | Moderate | High | Contingency
Likely | Major |  | Mitigate
Very Likely | Extreme |  | Transfer

## Heat Map Lookup (hidden)
| Trivial | Minor | Moderate | Major | Extreme
Rare | Low | Low | Low | Medium | Medium
Unlikely | Low | Low | Medium | Medium | Medium
Probable | Low | Medium | Medium | Medium | High
Likely | Medium | Medium | Medium | High | High
Very Likely | Medium | Medium | High | High | High